## Workplan Chart
MEE7012-SUM ¦ K-Value Impact on PETG & CF-PETG ¦ Workplan Chart
Student: | Vipul Kohinkar | Module: MEE7012-SUM |  |  |  | Academic Year: 2025-26
# | Task / Work Package | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
| Week commencing → | 25 May | 01 Jun | 08 Jun | 15 Jun | 22 Jun | 29 Jun | 06 Jul | 13 Jul | 20 Jul | 27 Jul | 03 Aug | 10 Aug | 17 Aug | 24 Aug | 31 Aug | 07 Sep
|  | Work Task |  |  | Milestone ▲ |  |  | University Closure
PLANNING & ADMINISTRATION
1 | Literature Review | bar: Module: MEE7012-SUM W1 25 May to Academic Year: 2025-26 W12 10 Aug
2 | Risk Assessment Form
3 | Project Description Form | bar: Module: MEE7012-SUM W2 01 Jun to Module: MEE7012-SUM W3 08 Jun
▲ | Milestone: Risk Assessment Submitted | bar: Module: MEE7012-SUM W1 25 May to Academic Year: 2025-26 W16 07 Sep
MATERIALS & PRINTER SETUP
4 | Material Order (PETG & CF-PETG) | bar: Module: MEE7012-SUM W2 01 Jun
5 | CAD Design – ISO 527-2 Type 5A Dog Bone
6 | Printer Setup & K Value Calibration | bar: Module: MEE7012-SUM W4 15 Jun to Academic Year: 2025-26 W5 22 Jun
▲ | Milestone: Materials Received | bar: Module: MEE7012-SUM W1 25 May to Academic Year: 2025-26 W16 07 Sep
3D PRINTING OF SPECIMENS
7 | Print PETG & CF-PETG Samples | bar: Module: MEE7012-SUM W1 25 May to Academic Year: 2025-26 W6 29 Jun; Academic Year: 2025-26 W9 20 Jul to Academic Year: 2025-26 W16 07 Sep
▲ | Milestone: All Samples Printed | bar: Module: MEE7012-SUM W1 25 May to Module: MEE7012-SUM W4 15 Jun; Academic Year: 2025-26 W6 29 Jun to Academic Year: 2025-26 W8 13 Jul; Academic Year: 2025-26 W10 27 Jul to Academic Year: 2025-26 W16 07 Sep
TESTING & ANALYSIS
8 | Tensile Testing | bar: Module: MEE7012-SUM W1 25 May to Academic Year: 2025-26 W8 13 Jul; Academic Year: 2025-26 W11 03 Aug to Academic Year: 2025-26 W16 07 Sep
9 | Optical Microscopy | bar: Module: MEE7012-SUM W1 25 May to Academic Year: 2025-26 W8 13 Jul; Academic Year: 2025-26 W11 03 Aug to Academic Year: 2025-26 W16 07 Sep
10 | University Closure (10 & 13 July)
11 | Data Analysis & Results Processing | bar: Module: MEE7012-SUM W1 25 May to Academic Year: 2025-26 W9 20 Jul; Academic Year: 2025-26 W13 17 Aug to Academic Year: 2025-26 W16 07 Sep
▲ | Milestone: Experimental Work Complete | bar: Module: MEE7012-SUM W1 25 May to Academic Year: 2025-26 W9 20 Jul; Academic Year: 2025-26 W11 03 Aug to Academic Year: 2025-26 W16 07 Sep
REPORT & PRESENTATION
12 | Report Writing
13 | Report Sub section outline submission | bar: Academic Year: 2025-26 W10 27 Jul
14 | Draft Report to Supervisior and Feedback | bar: Academic Year: 2025-26 W13 17 Aug
12 | Final Report Submission (27 Aug)
▲ | Milestone: Report Submitted | bar: Academic Year: 2025-26 W14 24 Aug; Academic Year: 2025-26 W16 07 Sep
16 | Presentation preparation
17 | Presentation submission | bar: Academic Year: 2025-26 W15 31 Aug
18 | Compulsory Presentation/ Interview | bar: Academic Year: 2025-26 W15 31 Aug to Academic Year: 2025-26 W16 07 Sep